## Sheet1
wp | activity | start_date | end_date | months
Research Aim 1 | SV data collection | 7 | 8 | 2
Research Aim 1 | SV data analysis | 8 | 10 | 3
Research Aim 1 | Coexpression data collection | 11 | 16 | 6
Research Aim 1 | Coexpression analysis | 12 | 20 | 9
Research Aim 1 | GWAS data collection | 11 | 16 | 6
Research Aim 1 | GWAS data analysis | 12 | 20 | 9
Research Aim 2 | Faba bean regeneration experiments | 2 | 21 | 20
Research Aim 2 | Functional analysis experiments | 20 | 34 | 15
misc | Personal | 1 | 1 | 1
misc | Writing | 33 | 36 | 4
misc | Writing | 20 | 22 | 3
misc | Confrence Presentation | 36 | 36 | 1
misc | Personal | 28 | 28 | 1
misc | Confrence Presentation | 17 | 17 | 1